## Risk log
Risk Assessment
Project name: JS Project
Project manager: Jabaran Khan
ID | Date raised | Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens. | Progress on actions
1 | 2022-08-08 | Not having the code function correctly | Medium | High | High | Me - Project Lead | Ensure that the code that is implement functions together between the front end and back end | Discuss with tutors if any issues have occurred during implentation. | Keeping checking and testing certain aspects of it. No issues have arisen so far.
2 | 2022-08-08 | Project design and deliverable definition is incomplete. | Medium | Medium | Medium | Me - Project Lead | Ensure that testing is done and no major bugs are outstanding | Keep testing the codes in intervals and ensure that it can be troubleshooted | Systems are working fine but will keep testing to ensure stability
3 | 2022-08-08 | Computer running slow | Medium | Medium | Low | Me - Project Lead | Laptop was running slow during the project as Chrome and Eclispe took quite a bit of RAM | Use my PC in case any issues arise | Was able to file transfer between laptop and PC. Due to Git Issues. Most of this has been done there.
| 2022-08-08 | Internet issues | Low | High | High | Me - Project Lead | Have back ups on Git as well as seeing alternative means of getting onto the internet | Contact trainers and discuss further options | No issues so far
4 | 2022-08-08 | Ensure full understanding of the code that is being implemented and that when it is delievered. | Medium | Medium | High | Me - Project Lead | Code can be explained on why it was implemented and what steps to were taken to do so. | Review code and leave comments on there so that it can be reviewed and checked by colleagues if desired | Everything has been understood so far and will keep reviewing in future
5 | 2022-08-08 | Getting burnt out | Medium | High | High | Me - Project Lead | Taking breaks when I can and as do not want to be burnt out by deadline | Ensure rest is taken but project is acceptable | Everything good so far with a little bit of caffiene
5 | 2022-08-08 | Getting Covid | High | High | High | Me - Project Lead | Caught Covid during project week - this has been impactful as I have not been at 100% | Ensure rest is taken when I can | Covid has made me unable to sleep so I have been using that to do the project

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High

## Dropdowns
High
Medium
Low